# Abonten — Implementation Timeline

Project start: Monday, July 6, 2026 → Go-live: January 29, 2027

# Section 1: Phase Overview

| Phase | Sprints | Weeks | Dates | Focus |
| --- | --- | --- | --- | --- |
| Phase 0 — Foundation | — | Wk 1–2 | Jul 6 – Jul 17 | Spec, architecture decisions, repo scaffold, CI/CD (mostly done) |
| Phase 1 — MVP | S1–S4 | Wk 3–10 | Jul 20 – Sep 11 | Inventory + basic booking + basic proof |
| Phase 2 — V1 | S5–S9 | Wk 11–20 | Sep 14 – Nov 20 | Full features: KPIs, campaign builder, marketplace, reporting |
| Phase 3 — V2 | S10–S13 | Wk 21–28 | Nov 23 – Jan 15 | Mobile/offline, bilingual, automation, beta |
| Phase 4 — Rollout | S14–S15 | Wk 29–30 | Jan 18 – Jan 29 | Production deploy, onboarding, training, go-live |

# Section 2: Sprint-by-Sprint Breakdown

| Sprint | Weeks | Dates | Deliverables |
| --- | --- | --- | --- |
| S1 | Wk 3–4 | Jul 20 – Jul 31 | Multi-tenant auth & org model, DB schema & migrations, base API scaffold, project structure |
| S2 | Wk 5–6 | Aug 3 – Aug 14 | Billboard inventory CRUD, approval workflow, listing lifecycle, basic marketplace search/filter/map |
| S3 | Wk 7–8 | Aug 17 – Aug 28 | Basic booking & reservations, availability, POP photo uploads, condition reports |
| S4 | Wk 9–10 | Aug 31 – Sep 11 | Client dashboard (campaign status, POP gallery), MVP integration testing, MVP release |
| S5 | Wk 11–12 | Sep 14 – Sep 25 | Bulk inventory import, multi-face structures, full spec schema, site metadata enrichment schema |
| S6 | Wk 13–14 | Sep 28 – Oct 9 | KPI estimation engine (impressions, reach, frequency, GRP/TRP, CPM, CPRP) |
| S7 | Wk 15–16 | Oct 12 – Oct 23 | Campaign builder (budget allocation, scheduling, scenarios, side-by-side comparison) |
| S8 | Wk 17–18 | Oct 26 – Nov 6 | Full marketplace & booking (availability calendar, pricing, reservations, conflict management), multi-currency |
| S9 | Wk 19–20 | Nov 9 – Nov 20 | Reporting & analytics module, V1 integration testing, V1 release |
| S10 | Wk 21–22 | Nov 23 – Dec 4 | Offline-first mobile apps (POP capture, field operator workflows) |
| S11 | Wk 23–24 | Dec 7 – Dec 18 | Bilingual EN/FR support, automated enrichment pipelines |
| S12 | Wk 25–26 | Dec 21 – Jan 1 | Automated spec validation, duplicate detection, API ecosystem integrations |
| S13 | Wk 27–28 | Jan 4 – Jan 15 | Security hardening, performance optimization, beta testing with OMG WeCA teams & media partners |
| S14 | Wk 29 | Jan 18 – Jan 22 | Production deployment, infrastructure, monitoring, observability |
| S15 | Wk 30 | Jan 25 – Jan 29 | Partner onboarding, user training, documentation, go-live |

# Section 3: Key Milestones

MVP — mid-Sep 2026 (inventory bookable, basic POP)

V1 — mid-Nov 2026 (full planning, KPIs, marketplace, reporting)

V2 beta — mid-Jan 2027 (mobile, bilingual, automation)

Go-live — end of Jan 2027

# Section 4: Summary

Total: ~30 weeks / 15 two-week sprints / ~7 months from start to rollout.